## Risk Register
risk_id | category | risk_statement | trigger | impact | likelihood(1-5) | severity(1-5) | risk_score | mitigation_controls | owner | status | next_review_date | notes
R-001 | Hallucination | Model returns an invented citation or reference. | Weak retrieval + poor guardrails | Severe reputational damage | 4 | 5 | 20 | Citations assembled from metadata only; abstain on weak evidence; regression tests | TBD | Open
R-002 | Theological/Boundary | Users interpret ‘Verified’ as a fatwa or authenticity verdict. | Ambiguous label UX | Misuse, backlash | 3 | 5 | 15 | Two-field output (match + evidence notes); explicit disclaimers; refusal policy | TBD | Open
R-003 | Licensing | Ingest/display texts without clear rights. | Unvetted sources | Legal risk, takedown | 3 | 5 | 15 | Corpus governance register; prototype-only lane until rights cleared; legal review | TBD | Open
R-004 | Translation mismatch | User text differs due to translation; system mislabels. | Multiple translations | False negatives/partials | 3 | 3 | 9 | Canonical Arabic anchor; store translation name; language-specific retrieval lanes | TBD | Open
R-005 | Duplicate narrations | Multiple similar narrations confuse output. | Overlapping hadith sources | User confusion | 3 | 3 | 9 | Duplicate clustering; show parallel narrations; avoid overclaiming | TBD | Open
R-006 | Abuse/Moderation | Tool used for sectarian attacks or extremist framing. | Adversarial prompts | Safety and reputational risk | 2 | 5 | 10 | Refusal policy, rate limits, monitoring, escalation workflow | TBD | Open
R-007 | Ask Engine / Expectation | Ask engine perceived as fatwa engine or authority source. | Users ask personal rulings | Backlash, misuse | 3 | 5 | 15 | Explicit disclaimers; refusal templates; no case-specific rulings | TBD | Open
R-008 | Ask Engine / Synthesis | Over-synthesis of contested interpretations into one definitive answer. | Multiple tafsir views | Theological risk | 3 | 5 | 15 | Attribution over synthesis; show multiple views; abstain on conflict | TBD | Open
R-009 | Ask Engine / Authority inflation | Fluent answer sounds more authoritative than evidence. | Thin evidence | Trust damage | 3 | 4 | 12 | Citations+snippets mandatory; confidence label; abstention thresholds | TBD | Open
R-010 | Program risk | Ask engine launched before verifier KPIs and governance maturity. | Scope pressure | Reputational blow-up | 3 | 5 | 15 | Formal phase gate; internal-only ask until thresholds met | TBD | Open

## Lookups
category | status
Hallucination | Open
Trust | Mitigating
Theological/Boundary | Closed
Licensing | Accepted
Moderation
Security
Privacy
Operational
Performance
Product